## April 1
|  |  | Weekly Sprint Sheet |  | Team Members | Email
Project: | 5 |  |  |  | Umer Qazi | uqazi2
Week Of: | 43577 |  |  |  | Farah Masood | mmasoo4
[5 empty] | Zaid Patel | zpatel24
[5 empty] | Mohammed Sami | msami4
Action Item | Item ID | Team Member | Last Week | This Week | Next Week | Issues
Set up GUI client server communication via serializable callback | p51 | Mohammed Sami |  | Set up callback code between server and client | Allowappropriate game play instructions to be displayed on client
Allow client to communicate letter choice to server | p52 | Farah Masood |  | set up 26 buttons on each client gui and disable buttons if not player's turn | allow letter choice to be properly communicated to server and update word blanks
regulate game play - keeping score, player turns, word being updated | p53 | Zaid Patel |  | set up a mechanism to keep accurat score | dictate player turns and updated word be reported to each client
Allow threading (four clients to connect to one server) | p54 | Umer Qazi |  | Allow server to handle 4 players maximum and minimum | after game is completed exit each client from server, and have 4 new clients connect to server for next game to begin